## Slide 1
NiChart
Neuro . Imaging . Chart
Project Group Meeting
NiChart Project Meeting, 09/29/2023
Presented by: Guray Erus
Artificial Intelligence in Biomedical Imaging Lab
(AIBIL – CBICA - UPENN)
Notes: 1

## Slide 2
1. Overview
Data collection, processing and model training

## Slide 3
Application on user data
Module 1
Image → Features
Module 2
Features → Biomarkers
Module 3
Biomarkers → Neuroimaging Chart

## Slide 4
2. Progress and Current Status
Module 1:
  sMRI processing (DLMUSE):
    Software package + Container
    Applied on complete ISTAGING data
    Validations completed (in comparison to MUSE + age trends/SPARE scores)
    AWS cloud module implemented and tested
  DTI and fMRI processing (QSIPrep, fMRIPrep, XCP):
    Software package + Container
    Adaptations to NiChart (ongoing)
    Applied on pilot ISTAGING data
  fMRI data driven components:
    Waiting for pre-processed data

## Slide 5
Module 2:
  Harmonization:
    Python software package
    New R based software package (with additional QC and vis. Tools)
    Application on ISTAGING data (Pending)
    AWS cloud module does not include harmonization (Pending)
  SPARE scores:
    from MUSE ROIs
    Generic SPARE package (SPARE-AD and SPARE-BA) from MUSE ROIs using multiple ML methods (SVM, Dense Network, etc.)
    Applied on pilot ISTAGING data
    AWS cloud module includes SPARE calculation
    fMRI and DTI based SPARE score calculation (work in progress)

## Slide 6
Module 3:
  Visualization:
    Client-side plotting of NiChart dimensions (java script)
    Pre-calculated centile values for ROIs and SPARE scores
    Bonus feature: Linking the plot to MRI image + segmentation label
    AWS cloud module implemented but not final (being linked)
  Reference data preparation:
    DLMUSE + SPARE + Centile calculation for pilot reference data
    Preparation for complete ISTAGING is work in progress

## Slide 7
3. Plans for the short term (0-3 months)
Completion of the web portal release version 1 (2/3 weeks)
Consolidation of data / code / documentation for release version 1 (+2 weeks)
Completion and submission of related papers (NiChart, DLMUSE) (2/3 weeks)
Activities for outreach and education (+ 4/6 weeks)
  Tools: Social media (Twitter / LinkedIn / Email / Zoom)
  Phases:
    Phase 1: Reach out to a limited group of potential users who can test and provide quick feedback
    Phase 2: Reach out to a larger group of users and collect feedback
    Phase 3: Organize online tutorial sessions
    Phase 4: Maintenance and plans for updates based on the feedback
    Phase 5: Submission for presentation in major conferences
  Major tasks for outreach:
    Preparation of active community resources integrated with the software packages;
    Collecting and analyzing data;
    Addressing issues, bugs, requests;
    Communication with users

## Slide 8
3. Plans for the mid-term (0-9 months)
Completion of data harmonization scripts and applications;
Final consolidation of reference data;
Integration of multi-modal image processing pipelines;
Optimization of user experience
  Faster processing, better visualizations, etc.
Extending imaging features and SPARE scores
  Calculating / integrating additional SPARE scores (CVD, SCZ, MD, DM, etc.);
  Developing image to SPARE models (i.e. bypassing ROI segmentation and data harmonization steps);
  Adding data driven image features (NMF components);
  Adding fast DL based voxelwise image features;
  Adding multi-modal SPARE scores;
  Adding heterogeneity subtypes (e.g. SmileGAN)

## Slide 9
Thank you ...