## Slide 1
NiChart meeting, 03/19/2024
Artificial Intelligence in Biomedical Imaging Lab
(AIBIL – CBICA - UPENN)
NiChart: Neuro Imaging Chart of AI-based Imaging Biomarkers
Year 2 milestones review – Status update

## Slide 2
Artificial Intelligence in Biomedical Imaging Lab
(AIBIL – CBICA - UPENN)
1
Agenda
2
3
4
Current status [1] – Pipelines
Current status [2] – Website / Portal
Current status [3] – Outreach / Dissemination
Future tasks

## Slide 3
Artificial Intelligence in Biomedical Imaging Lab
(AIBIL – CBICA - UPENN)
Current status [1] – Pipelines
sMRI pipelines:
  Skull stripping: Ready ✅
  MUSE Segmentation: Ready ✅ , some interface simplifications needed
  FSL Tissue Segmentation: Ready ✅
  White Matter Lesion Segmentation: To be done ❌
  sOPNMF parcellation: To be containerized 🚧
fMRI pipelines:
  fMRIPrep: Ready ✅
  XCP-D: Ready ✅
  pNet: Ready ✅ , need to move container to dockerhub
DTI pipelines:
  QSIPrep: Ready ✅
Harmonization:
  Package is ready in R, not sure if to be containerized / updated
  NiChart_Harmonize (?)
ML pipelines:
  SPARE scores: Ready ✅ (BA, AD)
  SurrealGAN: Ready ✅ (To be enabled)
  SmileGAN: Packaged, to be containerized 🚧
  Temporal Deep Kernel Gaussian Processes 🚧

## Slide 4
Artificial Intelligence in Biomedical Imaging Lab
(AIBIL – CBICA - UPENN)
Current status [2] – Website / Portal
Documentation – Components:
  Update with additional pipelines / models 🚧
  Double check links & make sure they correspond to the intended packages/docs ✅
Feedback:
  Survey?
  FAQ - update and add more questions / answers. 🚧
  Neurostars ❌
Contact:
  GitHub issues: ✅
  Contact page: ✅ , backend needs to be updated.
Fix out ‘Register’ bug that users get ‼️
Publications: ✅
About: ✅
Twitter: 🚧
Frontend:
  Visualization module much improved, overlay modal implemented ✅
  Working on updated multi-model interface for Image Processing and Machine Learning modules 🚧
AWS Backend:
  Created a query able DB of job containers to allow for an extensible model zoo ✅
  Currently working on connecting the scan / overlay modal to AWS filesystem 🚧

## Slide 5
Artificial Intelligence in Biomedical Imaging Lab
(AIBIL – CBICA - UPENN)
Current status [3] – Outreach / Dissemination
Presenting ac. Demo @ ISBI (May ‘24)
Presenting @ OHBM (June ‘24)
AAIC (?) (July ‘24)
Preparing proposal for RSNA (Nov – Dec ‘24)

## Slide 6
Artificial Intelligence in Biomedical Imaging Lab
(AIBIL – CBICA - UPENN)
Future tasks
Add more pipelines / models
  Cardiometabolic
  ASD & subtypes
  Age trajectories
  others
Improve website / portal interface
  Improve portal interface
  Maintain website content
Unify documentation, templates for repositories
  NiChart_template repo
  NiChart License
  Guide on package creation / containerization
  Guide on documentation
Automate reference data creation for upcoming models / pipelines
  Use airflow
Locally installable tool
Provide online tutorials, demos (schedule)
Neurostars educational material / community presence
Improve twitter activity